## UNCOILER COIL CAR ASSY
Project: N - 2544 - APL - CR REWINDING LINE 750 MM @ 200 MPM |  | Task: COIL CAR @ UNCOILER - Ordering & Manufacturing |  | Subtask: UNCOILER COIL CAR ASSY
Sr. No | Joblist | Dwng No | Quantity | Material | Wt | Assembly Name | Vendor Name | PO Number | Price | Release of PO |  | Ready for Assembly
[10 empty] | Status | Date | Status | Date
1 | TOP FRAME | 2402-CAR-01-01-01-000 | 1 | WELDED STEEL | 360.3 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 | 358000 | CO | 23-Apr-26 | NS | 21-Aug-26
2 | BOTTOM FRAME | 2402-CAR-01-01-02-000 | 1 | WELDED STEEL | 401.4 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
3 | GUIDE ROD | 2402-CAR-01-01-03-000 | 2 | AS PER DRAWING | 84 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
4 | MOTOR FRAME | 2402-CAR-01-01-04-000 | 1 | WELDED STEEL | 10.2 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
5 | DUPLEX CHAIN, PITCH 1" (25.4mm), 1220MM LONG, MAKE- RENOLD | 2402-CAR-01-01-05-000 | 1 | STD. | 11.7 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
6 | BEARING BLOCK- 1 | 2402-CAR-01-01-06-000 | 2 | M.S | 24.1 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
7 | HYDRAULIC MOTOR,OMT- 315,DANFOSS | 2402-CAR-01-01-07-000 | 1 | STD. | 22.5 | UNCOILER COIL CAR ASSY | INDTOOLS | 4500014981 | 51500 | CO | 23-Apr-26 | NS | 21-Aug-26
8 | BEARING BLOCK- 2 | 2402-CAR-01-01-08-000 | 2 | M.S | 24.3 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
9 | HYD. CYL. BORE- Ø200,ROD-Ø140,STK- 1000mm,FF | 2402-CAR-01-01-09-000 | 1 | STD. | 310.8 | UNCOILER COIL CAR ASSY | HYDMARK | 4500014988 | 108604.50 | CO | 23-Apr-26 | NS | 21-Aug-26
10 | L.H. WHEEL SHAFT | 2402-CAR-01-01-00-001 | 1 | EN-9 | 50 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
11 | R.H. WHEEL SHAFT | 2402-CAR-01-01-00-002 | 1 | EN-9 | 47.4 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
12 | WHEEL | 2402-CAR-01-01-00-003 | 2 | EN-9 | 40.3 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
13 | PAD | 2402-CAR-01-01-00-004 | 4 | NYLON | 18.2 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
14 | CLEVIS | 2402-CAR-01-01-00-005 | 1 | M.S | 22.9 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
15 | BUSH | 2402-CAR-01-01-00-006 | 2 | GUN METAL | 5.4 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
16 | RETAINER- 2 | 2402-CAR-01-01-00-007 | 2 | M.S | 2.8 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
17 | RETAINER- 1 | 2402-CAR-01-01-00-008 | 2 | M.S | 2.7 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
18 | WHEEL SPROCKET | 2402-CAR-01-01-00-009 | 1 | EN-9 | 3.5 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
19 | END PLATE (MOTOR) | 2402-CAR-01-01-00-010 | 1 | M.S | 0.3 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
20 | WHEEL | 2402-CAR-01-01-00-011 | 2 | EN-9 | 37.4 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
21 | END PLATE | 2402-CAR-01-01-00-012 | 4 | M.S | 0.6 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
22 | SPACER | 2402-CAR-01-01-00-013 | 1 | EN-9 | 0.1 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
23 | SPACER | 2402-CAR-01-01-00-014 | 4 | EN-9 | 1.2 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
24 | MOTOR SPROCKET | 2402-CAR-01-01-00-015 | 1 | EN-9 | 4.1 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
25 | COIL CAR CHAIN COVER | 2402-CAR-01-01-00-016 | 1 | M.S | 3.6 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
26 | BEARING,SPHERICAL, 22218 E ,SKF (SPHERICAL ROLLER BRG 90IDx160ODx40THK. mm) | 22218_E | 4 | STD. |  | UNCOILER COIL CAR ASSY | EASTERN | 4500014980 | 8848 | CO | 23-Apr-26 | NS | 21-Aug-26
27 | OIL SEAL-105ID x 130OD x 10THK (AIA1050819) | 105X130X10_AIA10508 19_OIL | 8 | STD. | 0.4 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
28 | GREASE NIPPLE 1/8" BSP | Grease Nipple 1-8 BSP | 8 | STD. |  | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
29 | SHEAR BLOCK- 15X15X80MM | STOPPER 15X15X80 | 32 | M.S | 0.1 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
30 | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | is 1363(part2) - m10 x 35-nn | 10 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
31 | Spring Lock Washer IS 6735 - 10 | is 6735- 10 | 18 | MS | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
32 | Plain Washer (Type A) IS 2016 - 11 | is 2016 a- 11 | 18 | MS | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
33 | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | is 1363(part2) - m16 x 55-nn | 4 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
34 | Plain Washer (Type A) IS 2016 - 18 | is 2016 a- 18 | 20 | MS | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
35 | Spring Lock Washer IS 6735 - 16 | is 6735- 16 | 4 |  | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
36 | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | is 1363(part2) - m12 x 45-nn | 5 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
37 | Plain Washer (Type A) IS 2016 - 14 | is 2016 a- 14 | 5 |  | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
38 | Spring Lock Washer IS 3063 - 12-A | IS 3063- 12-A | 4 | MS | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
39 | Socket Head Cap Screw IS 2269 - M10 x 25 | is 2269 - m10 x 25-n | 16 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
40 | Spring Lock Washer IS 6735 - 12 | is 6735- 12 | 1 |  | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
41 | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | IS 1363(Part2) - M24 x 80-NC | 8 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
42 | Plain Washer (Type A) IS 2016 - 26 | IS 2016 A- 26 | 16 | MS | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
43 | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | IS 1363(Part2) - M24 x 90-NC | 8 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
44 | Socket Head Cap Screw IS 2269 - M10 x 35 | IS 2269 - M10 x 35-C | 16 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
45 | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | is 1363(part2) - m16 x 65-nn | 16 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
46 | Spring Lock Washer IS 3063 - 16-A | is 3063- 16-a | 16 | MS | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
47 | Plain Washer (Type A) IS 2016 - 33 | IS 2016 A- 33 | 8 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
48 | Spring Lock Washer IS 6735 - 30 | IS 6735- 30 | 8 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
49 | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | IS 1363(Part2) - M10 x 40-WC | 8 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26
50 | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 110 | IS 1363(Part2) - M30 x 110-NC | 8 | 0 | 0 | UNCOILER COIL CAR ASSY | GLOBAL | 4500014975 |  | CO | 23-Apr-26 | NS | 21-Aug-26